## Instructions
OMS IT & Information Security Risk Governance - Action Plan
Scope
This tracker breaks Redmine #179 (governance/main ticket), #186 (periodic risk-assessment gap) and #188 (monitoring & measurement gap) into concrete, assignable tasks. It is the working companion to 'OMS_IT_InfoSec_Risk_Policy_and_Procedure.docx' and 'OMS_Master_IT_Security_Risk_Register.xlsx'.
How to use this workbook
1. Work the 'Action Plan' tab top to bottom - it is sequenced so later tasks depend on earlier ones (see the Dependency column).
2. 'Requires System/Login Access' flags tasks that need Coolify, cloud console, firewall, or other live-system access. Everything flagged 'No' can be done today from documentation alone.
3. Suggested dates assume a start date of 22 July 2026 and are placeholders - adjust to the owners' real availability once assigned.
4. Update Status as work progresses. Overdue items are highlighted automatically once you pass the Due Date without marking a status of Done.
5. This plan does not replace the Risk Register - baseline risk assessment tasks here produce the rows that go into the register.
Today's priority (no system access required)
Governance role appointments, policy/criteria ratification, monitoring catalogue definition, review/report templates, and the risk-treatment/escalation/acceptance workflows can all be completed today without logging into Coolify or any live system. Log-source onboarding, alert build/testing, and infrastructure-dependent parts of the baseline assessment are flagged 'Yes' and should wait until you have that access.

## Action Plan
Task ID | Ticket | Workstream | Task | Output / Evidence | Owner | Requires System/Login Access | Dependency | Priority | Start Date | Due Date | Status | Notes
T-001 | #179 | Governance | Appoint Executive Risk Owner, Process Owner and Information Security Risk Coordinator | Names recorded in policy Section 2 and communicated | [MD/Exec Team] | No | - | Critical | 2026-07-22 | 2026-07-24 | Not Started
T-002 | #179 | Governance | Circulate draft Policy & Procedure for review and MANCO approval | Approved, version-controlled policy in SharePoint | Process Owner | No | T-001 | Critical | 2026-07-23 | 2026-07-27 | Not Started
T-003 | #179 | Governance | Ratify risk appetite, likelihood/impact/rating and acceptance criteria | Signed-off criteria (policy Section 4) | Executive Risk Owner / MANCO | No | T-002 | High | 2026-07-24 | 2026-07-29 | Not Started
T-004 | #179 | Governance | Confirm controlled SharePoint site, library structure, permissions and retention | SharePoint site live with access list | Process Owner | No | T-001 | High | 2026-07-23 | 2026-07-26 | Not Started
T-005 | #179 | Register | Populate Risk Register with known risks from prior pen-test findings and audit history | Risk Register rows R-0002 onward | Process Owner | No | - | Critical | 2026-07-22 | 2026-07-27 | Not Started
T-006 | #179 | Register | Pull asset/ownership data from #438 asset register into risk register (Asset/Owner fields) | Register rows linked to #438 assets | Process Owner | Yes - Coolify/Cloud | #438 completion | High | 2026-07-27 | 2026-08-03 | Not Started
T-007 | #179 | Baseline Assessment | Assess identity, access, MFA, privileged and service accounts | Risk entries + evidence links | IT Infrastructure Lead | Yes - Coolify/Cloud | T-005 | Critical | 2026-07-28 | 2026-08-04 | Not Started
T-008 | #179 | Baseline Assessment | Assess source code, CI/CD, deployment and software supply-chain controls | Risk entries + evidence links | Engineering Lead | Yes - Coolify/Cloud | T-005 | High | 2026-07-28 | 2026-08-06 | Not Started
T-009 | #179 | Baseline Assessment | Assess dev/test/demo/production environment separation | Risk entries + evidence links | Engineering Lead | Yes - Coolify/Cloud | T-005 | High | 2026-07-28 | 2026-08-06 | Not Started
T-010 | #179 | Baseline Assessment | Assess secrets and organisational API-key ownership | Risk entries + evidence links | Engineering Lead | Yes - Coolify/Cloud | T-005 | Critical | 2026-07-28 | 2026-08-04 | Not Started
T-011 | #179 | Baseline Assessment | Assess backups, recovery, DR and business continuity | Risk entries + evidence links | IT Infrastructure Lead | Yes - Coolify/Cloud | T-005 | Critical | 2026-07-28 | 2026-08-06 | Not Started
T-012 | #179 | Baseline Assessment | Assess M365, SharePoint, email, domains and DNS | Risk entries + evidence links | IT Infrastructure Lead | Yes - M365/SharePoint | T-005 | High | 2026-07-28 | 2026-08-06 | Not Started
T-013 | #179 | Baseline Assessment | Assess cloud, Coolify, databases, storage and third-party platforms | Risk entries + evidence links | IT Infrastructure Lead | Yes - Coolify/Cloud | T-005 | Critical | 2026-07-28 | 2026-08-06 | Not Started
T-014 | #179 | Baseline Assessment | Assess OBSE, CVEvolve and other OMS-managed applications and APIs | Risk entries + evidence links | Engineering Lead | Yes - Coolify/Cloud | T-005 | High | 2026-07-28 | 2026-08-06 | Not Started
T-015 | #179 | Baseline Assessment | Assess POPIA, retention and third-party processing obligations | Risk entries + evidence links | Compliance/Process Owner | No | T-005 | High | 2026-07-24 | 2026-08-01 | Not Started
T-016 | #179 | Baseline Assessment | Assess AI/model, dataset, prompt-injection and model-supply-chain risks | Risk entries + evidence links | Engineering Lead | No | T-005 | Medium | 2026-07-25 | 2026-08-03 | Not Started
T-017 | #179 | Baseline Assessment | Assess skills, capacity, key-person and succession risk | Risk entries + evidence links | Executive Risk Owner | No | T-005 | Medium | 2026-07-25 | 2026-08-01 | Not Started
T-018 | #179 | Baseline Assessment | Assess devices, laptops, physical security and remote access | Risk entries + evidence links | IT Infrastructure Lead | Yes - Coolify/Cloud | T-005 | Medium | 2026-07-28 | 2026-08-06 | Not Started
T-019 | #179 | Baseline Assessment | Assess internet-facing infrastructure, network exposure and pen-test remediation status | Risk entries + evidence links | IT Infrastructure Lead | Yes - Network/Firewall | T-005 | Critical | 2026-07-28 | 2026-08-04 | Not Started
T-020 | #179 | Treatment | Build Risk Treatment Plan (owners, actions, target dates) from register | Risk Treatment Plan document/tab | Process Owner | No | T-005 to T-019 | High | 2026-08-03 | 2026-08-09 | Not Started
T-021 | #179 | Process | Design residual-risk acceptance workflow and approval record | Documented workflow + template | Process Owner | No | T-003 | Medium | 2026-07-25 | 2026-07-30 | Not Started
T-022 | #179 | Process | Design risk escalation and overdue-action procedure | Documented procedure | Process Owner | No | T-003 | Medium | 2026-07-25 | 2026-07-30 | Not Started
T-023 | #186 | Reviews | Design monthly risk-review template and review calendar | Template + calendar invite | Process Owner | No | T-003 | Critical | 2026-07-24 | 2026-07-28 | Not Started
T-024 | #186 | Reviews | Conduct and evidence the first monthly risk review | Meeting record, decisions, updated register | Process Owner | No | T-023, T-020 | Critical | 2026-08-10 | 2026-08-12 | Not Started
T-025 | #179 | Reporting | Design MANCO risk dashboard/report template | Report template | Process Owner | No | T-003 | High | 2026-07-24 | 2026-07-28 | Not Started
T-026 | #179 | Reporting | Present first risk report to MANCO | MANCO meeting record with decisions | Executive Risk Owner | No | T-025, T-024 | Critical | 2026-08-12 | 2026-08-16 | Not Started
T-027 | #179 | Evidence & Training | Define evidence-retention requirements for risk records | Retention schedule | Process Owner | No | T-004 | Medium | 2026-07-24 | 2026-07-28 | Not Started
T-028 | #179 | Evidence & Training | Schedule staff and risk-owner awareness/training session | Training record/attendance | Process Owner | No | T-002 | Low | 2026-07-27 | 2026-08-11 | Not Started
T-029 | #188 | Monitoring Catalogue | Define monitoring catalogue: events, controls, metrics, data sources, owners, thresholds, review frequency | Approved monitoring catalogue | Process Owner / Security Lead | No | - | Critical | 2026-07-22 | 2026-07-27 | Not Started
T-030 | #188 | Monitoring Catalogue | Define log retention, access control, integrity protection, time-sync and privacy requirements | Documented log-handling standard | Security Lead | No | T-030 | High | 2026-07-25 | 2026-07-29 | Not Started
T-031 | #188 | Monitoring Catalogue | Define alert ownership, escalation, incident-ticket creation and evidence-preservation process | Documented alerting process | Security Lead | No | T-030 | High | 2026-07-25 | 2026-07-29 | Not Started
T-032 | #188 | Monitoring Catalogue | Produce monthly monitoring report template and link to #179 MANCO review | Report template | Security Lead | No | T-025 | Medium | 2026-07-26 | 2026-07-30 | Not Started
T-033 | #188 | Implementation | Onboard firewall, reverse-proxy, DNS, auth, OS, application, database, mail and cloud logs | Log sources centralised and verified | IT Infrastructure Lead | Yes - Coolify/Cloud | T-030 | Critical | 2026-07-30 | 2026-08-09 | Not Started
T-034 | #188 | Implementation | Build alerts and tested playbooks for exposed services, injection, cache poisoning, malicious upload, DNS/egress anomalies, credential misuse, backup/restore abuse | Alerts + playbooks configured | Security Lead | Yes - Coolify/Cloud | T-034 | Critical | 2026-08-03 | 2026-08-13 | Not Started
T-035 | #188 | Implementation | Test alerts via authorised simulation and record evidence | Test evidence + escalation proof | Security Lead | Yes - Coolify/Cloud | T-035 | High | 2026-08-11 | 2026-08-16 | Not Started

## Lists (hidden)
Ticket | Priority | Status | AccessReq
#179 | Critical | Not Started | No
#186 | High | In Progress | Yes - Coolify/Cloud
#188 | Medium | Blocked | Yes - Network/Firewall
#179 / #186 | Low | Done | Yes - M365/SharePoint
#179 / #188